## Slide 1
CORPORATE STRATEGY — ILLUSTRATIVE SAMPLE
Cost Transformation Roadmap
A phased path to a 15% reduction in the addressable cost base within six quarters.

## Slide 2
WHERE THE COST BASE SITS TODAY
The base skews structural, not one-off
Cost Transformation Roadmap — Illustrative sample, confidential
2
$340M
Total addressable cost base
62%
Sits in G&A and shared services
15%
Target reduction, run-rate
Roughly two-thirds of the base is structural spend across shared services and corporate functions, rather than discretionary or project cost — which is why the roadmap sequences process and organization changes ahead of one-off cuts.

## Slide 3
IMPLEMENTATION SEQUENCE
Three phases sequence quick wins ahead of structural change
Cost Transformation Roadmap — Illustrative sample, confidential
3
Phase 1 · Q1–Q2
Quick wins
Procurement renegotiation and vendor consolidation across the top 20 suppliers.
Phase 2 · Q3–Q4
Process redesign
Standardize and automate transaction-heavy processes across shared services.
Phase 3 · Q5–Q6
Organization reset
Reduce management layers and widen span of control in corporate functions.

## Slide 4
EXPECTED IMPACT
Savings ramp fastest once phase two lands
Cost Transformation Roadmap — Illustrative sample, confidential
4
Chart: $M, cumulative
| Q1 | Q2 | Q3 | Q4 | Q5 | Q6
Cumulative run-rate savings ($M) | 4 | 11 | 24 | 38 | 46 | 51

## Slide 5
Recommendation
Approve phase one now
Procurement and vendor consolidation can start within 30 days with no organizational change required.
Stand up a PMO
A small transformation office to track savings against target and clear cross-functional blockers.
Review at Q2
Confirm phase two scope once quick-win savings are banked and validated by finance.
Cost Transformation Roadmap — Illustrative sample, confidential
5